## Framework Tasks
Task | Estimate in Hours | Comments
Solution Structure & Project Creation | 8
OAuth2.0 Implementation | 16 | Basic setup using IdentityServer3
Social Media/External Login Providers Configuration | 8
OAuth2.0 Flows Implementation | 12 | Different client-server flows to accommodate various login mechanisms.
Logging Component Implementation | 4 | Log4Net implementation to enable exception/error logging.
Ciserro Scheduler Service | 24 | A windows service using which we could configure batch jobs, notifications etc. This task deals with creating the stubs and core components ready.
Email Component Implementation | 4
Entity Framework Code First Setup & Implementation | 8
Media Management Module | 16 | Manages image/video uploads, downloads etc.
Payment Gateway Configuration |  | Need to finalize the payment gateway that we're going to use and the different types of payment options we provide.
Data Sync/Migration from Govt website |  | This needs more inputs from the client to understand the kind of data that we're dealing with.
Total | 100

## Module Tasks
USE CASE ID | TITLE | BEST | LIKELY | WORST
CONSUMER
Ciserro_UC_1 | Consumer registration
API |  | 4 | 6 | 6
DB |  | 1 | 2 | 2
Email Verification |  | 4 | 6 | 6
Web
Ciserro_UC_1.1 | Consumer Social Sign up
Registration UI & Wireup |  | 8 | 10 | 10
Identity server setup |  | 4 | 8 | 8
DB |  | 1 | 2 | 2
Social media app setup |  | 4 | 8 | 8
Web
Ciserro_UC_2 | Consumer Sign In
API |  | 4 | 6 | 6
DB |  | 1 | 2 | 2
Web
Ciserro_UC_3 | Consumer Social Sign In
API |  | 4 | 6 | 6
Identity server setup |  | 4 | 8 | 8
DB |  | 1 | 2 | 2
Web
Ciserro_UC_4 | Search a facility
API |  | 6 | 8 | 8
Web
Ciserro_UC_5 | Advanced Facility Search
API |  | 6 | 8 | 8
Web
Ciserro_UC_6 | Viewing Search Results
Web
Ciserro_UC_7 | Navigate to Facility Details
API |  | 4 | 6 | 6
Web
Ciserro_UC_8 | Request a Tour Facility Site
API |  | 6 | 8 | 8
Payment Processing |  | 6 | 8 | 10
Email Notification |  | 2 | 4 | 4
DB |  | 1 | 2 | 2
Web
Ciserro_UC_37 | Filter Facility After Search
Web
Ciserro_UC_9 | Reserve Facility
API |  | 6 | 8 | 8
Payment Processing |  | 6 | 8 | 10
Email Notification |  | 2 | 4 | 4
DB |  | 1 | 2 | 2
Web
Ciserro_UC_10 | Rate a Facility
API |  | 4 | 6 | 6
DB |  | 1 | 2 | 2
Web
Ciserro_UC_11 | Review a Facility
API |  | 4 | 6 | 6
DB |  | 1 | 2 | 2
Web
Ciserro_UC_12 | Raise a Complaint Facility
API |  | 4 | 6 | 6
DB |  | 1 | 2 | 2
Email Notification |  | 2 | 3 | 4
Web
Ciserro_UC_13 | Save a Facility
API |  | 2 | 4 | 4
DB |  | 1 | 2 | 2
Web
Ciserro_UC_14 | Email to Facility Provider
API |  | 2 | 4 | 4
Email Notification |  | 2 | 4 | 4
Web
FACILITY SUPERVISOR
Ciserro_UC_15 | Facility Supervisor Registration
API |  | 2 | 4 | 6
DB |  | 1 | 2 | 2
Web
Ciserro_UC_16 | Facility Registration
API |  | 4 | 8 | 10
DB |  | 1 | 2 | 2
Email Notification |  | 2 | 4 | 4
Web
OTP (Not Confirmed)
Ciserro_UC_17 | View Facility Details
API |  | 2 | 4 | 6
DB
Web
Ciserro_UC_18 | Update Facility Details
API |  | 12 | 24 | 32
DB |  | 2 | 4 | 6
Email Notification (Not Confirmed) |  | 2 | 4 | 4
Web
Ciserro_UC_19 | Initiate Mothly Payment
API |  | 2 | 4 | 6
DB |  | 2 | 4 | 6
Payment Processing |  | 2 | 4 | 6
Web
Ciserro_UC_20 | View Appointment/Reservation
API (Appointments) |  | 2 | 4 | 6
API (Reservations) |  | 2 | 4 | 6
Ciserro_UC_21 | Promote a Facility
API |  | 2 | 4 | 6
DB |  | 1 | 2 | 4
Payment Processing |  | 2 | 4 | 6
Email Notification |  | 2 | 4 | 4
Web
Ciserro_UC_22 | View Dashboard
API |  | 4 | 8 | 10
Web
Ciserro_UC_23 | View Facility Reviews
API |  | 2 | 4 | 6
Web
Ciserro_UC_33 | Facility Supervisor Sign In
API
Ciserro_UC_35 | Post Reviews
API |  | 2 | 8 | 12
ADMINISTRATOR
Ciserro_UC_34 | Administrator Sign In
Ciserro_UC_24 | View DashBoard - Administrator
API |  | 4 | 8 | 10
Web
Ciserro_UC_25 | View Facility Registration Requests
API |  | 2 | 4 | 6
Web
Ciserro_UC_26 | Approve Facility Registration Request
API |  | 2 | 4 | 6
DB |  | 1 | 2 | 2
Email Notification |  | 2 | 4 | 4
Ciserro_UC_27 | Reject Facility Registration Request
API
DB
Email Notification
Ciserro_UC_28 | View Consumer Complaints
API |  | 2 | 4 | 6
Web
Ciserro_UC_29 | View Facility Payment Dues
API |  | 4 | 6 | 8
Web
Ciserro_UC_30 | View Facility Feature Requests
API |  | 2 | 4 | 6
Web
Ciserro_UC_31 | Approve Facility Feature Requests
API |  | 2 | 4 | 6
DB |  | 1 | 2 | 2
Email Notification |  | 2 | 4 | 4
Web
Ciserro_UC_32 | Reject Facility Feature Requests
API
DB
Email Notification
Web
Ciserro_UC_36 | Create Facility
API |  | 4 | 8 | 10
DB |  | 1 | 2 | 2
Web
Ciserro_UC_38 | View Reports
API
DB
Web
Ciserro_UC_39 | View/Edit/Delete Facility Provider
API (Provider List) |  | 2 | 4 | 6
API (Provider Details) |  | 2 | 4 | 6
API (Update) |  | 4 | 8 | 10
API (Delete) |  | 2 | 4 | 6
Email Notification
Ciserro_UC_40 | View and Search Registered Consumers
API (Cosumers List) |  | 2 | 4 | 6
API (Search Consumer) |  | 4 | 8 | 12
Web
Ciserro_UC_41 | Review Document - Facility Provider
API |  | 1 | 2 | 4
Web
Ciserro_UC_42 | User Remove a Facility
API |  | 1 | 2 | 4
DB |  | 1 | 1 | 1
Email Notification |  | 2 | 2 | 2
Web
OTHER MODULES
Database Design
Server Configuration