## Sheet1
Sl.No | Task | Estimate in Hours | Comments
1 | Consumer Registration
| Registration API Method | 4
| Email Verification | 4
Social Media - Sign up
| Registration UI & Wireup | 8
| Identity server Setup | 4
| Social Media Apps Setup | 4
User - Sign In
| API Method | 4
User - Sign In using Social Media
| Identity Server Configuration | 4
Facility Search - Basic
| API Method | 6
Facility Search - Advanced
| API Method | 6
Facility Details
| API Method | 4
Facility Tour
| API Method | 6
| Payment Processing | 6
| Email Notification | 2
Facility Reserve
| API Method | 4
| Payment Processing | 4
| Email Notification | 2
Facility Rating
| API Method | 4
Facility Review
| API Method | 4
Facility Complaint
| Api Method | 4
| Email Notification | 2
Save Facility
| API Method | 2
Email Facility Supervisor
| Api Method | 2